## Slide 1: Future Strategy and Work Plan
IESBA CAG Meeting
September 11, 2013
New York
Ken Siong, IESBA Technical Director

## Slide 2: Background
January 2013 strategy survey
April 2013 CAG: high-level overview of survey responses
May 2013 NSS discussion
IESBA consideration of survey responses June 2013
Key tentative decisions
  Maintain current work plan but extend 2011-2012 SWP to end of 2014
  Articulate longer term vision for strategy to guide Board actions
  Shortlist of possible projects identified for further consideration

## Slide 3: Draft SWP Consultation Paper
To be considered at IESBA meeting next week
Proposal to extend strategy period to four years from current three
  SWP 2015-2018
Four strategic themes proposed
  Promoting and facilitating adoption and implementation
  Maintaining high-quality Code for global application
  Evolving Code for continued relevance in changing environment
  Increasing engagement and cooperation with stakeholders

## Slide 4: Draft SWP CP – Key Considerations
Some current projects / initiatives to extend into 2015 and beyond
A number of factors guiding identification of potential actions and priorities, e.g.
  Potential benefits to the public interest
  Extent to which public trust and confidence in profession will be further enhanced
Need to maintain flexibility important
Key assumption: high priority and resource allocation to Structure of the Code work

## Slide 5: Draft SWP CP – Key Proposed Actions
Prioritize Structure of the Code work
Address enforceability and related matters
Develop greater understanding of extent of adoption of 2009 Code
Maintain strong focus on stakeholder outreach
Review guidance regarding safeguards in the Code
Undertake broad review of topic of fee dependency
Explore guidance on topic of collective investment vehicles

## Slide 6: Forward Timeline
IESBA consideration of draft CP Sept 2013
PIOB approval of extension of 2011-2012 SWP Nov 2013
IESBA approval of CP Dec 2013
CAG update March 2014
IESBA consideration of CP responses April 2014
NSS discussion May 2014
IESBA first-read of revised SWP July 2014
CAG discussion Sept 2014
Final IESBA approval Oct 2014

## Slide 7: Matters for Consideration
Are the proposed strategic themes appropriate?
Do the potential actions identified represent appropriate priorities for the period?
Are the relative priorities of identified actions appropriate?
Are there actions not identified that should be included?
Are there any other matters that the Board should consider in finalizing CP?